## Sheet1
Features | Notes | Code_and_Unit_Testing | Design | Testing_and_Debugging | BA | Total | Buffered | Effort
Export plans | - User should be able to export lesson(s) | 56 | 11.2 | 16.8 | 14 | 98 | 98 | H
Sync with main online server | - All contents and lessons will be housed in a central server. | 567 | 113.4 | 170.1 | 141.75 | 992.25 | 992.25 | H
Manual Grading for Objective Assessment | - All contents and lessons will be housed in a central server. | 24 | 4.8 | 7.2 | 6 | 42 | 42 | M
Assessment status | - All contents and lessons will be housed in a central server. | 10 | 2 | 3 | 2.5 | 17.5 | 17.5 | M
Rename assessments | - All contents and lessons will be housed in a central server. | 4 | 0.8 | 1.2 | 1 | 7 | 7 | L
Add Academic Cooridnator role | - All contents and lessons will be housed in a central server. | 70 | 14 | 21 | 17.5 | 122.5 | 122.5 | H
Rename Local admin and Teacher | - All contents and lessons will be housed in a central server. | 8 | 1.6 | 2.4 | 2 | 14 | 14 | M
Media player | - User would like to play the video content that is stored locally in a server. The media player will let the user a video thats available in the resource library or lesson. | 407 | 81.4 | 122.1 | 101.75 | 712.25 | 712.25 | H
|  | 0 | 0 | 0 | 0 | 0 | 0 | L
|  | 0 | 0 | 0 | 0 | 0 | 0 | L
|  | 0 | 0 | 0 | 0 | 0 | 0 | L
|  | 0 | 0 | 0 | 0 | 0 | 0 | L
|  | 0 | 0 | 0 | 0 | 0 | 0 | L
|  | 0 | 0 | 0 | 0 | 0 | 0 | L
|  | 0 | 0 | 0 | 0 | 0 | 0 | L
|  | 0 | 0 | 0 | 0 | 0 | 0 | L
|  | 0 | 0 | 0 | 0 | 0 | 0 | L
|  | 0 | 0 | 0 | 0 | 0 | 0 | L
|  | 0 | 0 | 0 | 0 | 0 | 0 | L
|  | 0 | 0 | 0 | 0 | 0 | 0 | L
|  | 0 | 0 | 0 | 0 | 0 | 0 | L
|  | 0 | 0 | 0 | 0 | 0 | 0 | L
|  | 0 | 0 | 0 | 0 | 0 | 0 | L
|  | 0 | 0 | 0 | 0 | 0 | 0 | L
|  | 0 | 0 | 0 | 0 | 0 | 0 | L
|  | 0 | 0 | 0 | 0 | 0 | 0 | L
|  | 0 | 0 | 0 | 0 | 0 | 0 | L
|  | 0 | 0 | 0 | 0 | 0 | 0 | L
|  | 0 | 0 | 0 | 0 | 0 | 0 | L
|  | 0 | 0 | 0 | 0 | 0 | 0 | L
|  | 0 | 0 | 0 | 0 | 0 | 0 | L
|  | 0 | 0 | 0 | 0 | 0 | 0 | L
|  | 0 | 0 | 0 | 0 | 0 | 0 | L
|  | 0 | 0 | 0 | 0 | 0 | 0 | L
|  | 0 | 0 | 0 | 0 | 0 | 0 | L
|  | 0 | 0 | 0 | 0 | 0 | 0 | L
|  | 0 | 0 | 0 | 0 | 0 | 0 | L
|  | 0 | 0 | 0 | 0 | 0 | 0 | L
|  | 0 | 0 | 0 | 0 | 0 | 0 | L
|  | 0 | 0 | 0 | 0 | 0 | 0 | L
|  | 0 | 0 | 0 | 0 | 0 | 0 | L
|  | 0 | 0 | 0 | 0 | 0 | 0 | L
Total |  | 1146.0 | 229.2 | 343.8 | 286.5 | 2005.5 | 2005.5

## Sheet2
Particulars | Effort
Development | 1146
Design | 229.2
Testing | 343.8
BA | 286.5