## Sheet1
Features | Notes | Code and Unit Testing | Design | Testing and Debugging | BA | Total | Buffered | Effort
Export plans | - User should be able to export lesson(s) in a suitable format and import these lessons in other instances of ABC LMS in other locations. Weeeee | 180 | 36 | 54 | 45 | 315 | 315 | H
Sync with main online server | - All contents and lessons will be housed in a central server. | 240 | 48 | 72 | 60 | 420 | 0 | H
Manual Grading for Objective Assessment | - All contents and lessons will be housed in a central server. | 24 | 4.8 | 7.2 | 6 | 42 | 42 | M
Assessment status | - All contents and lessons will be housed in a central server. | 10 | 2 | 3 | 2.5 | 17.5 | 17.5 | M
Rename assessments | - All contents and lessons will be housed in a central server. | 4 | 0.8 | 1.2 | 1 | 7 | 7 | L
Add Academic Cooridnator role | - All contents and lessons will be housed in a central server. | 70 | 14 | 21 | 17.5 | 122.5 | 122.5 | H
Rename Local admin and Teacher | - All contents and lessons will be housed in a central server. | 8 | 1.6 | 2.4 | 2 | 14 | 14 | M
Media player | - User would like to play the video content that is stored locally in a server. - The media player will let the user play/pause/seek a video that's available in the resource library or lesson. | 40 | 8 | 12 | 10 | 70 | 70 | M
Total |  | 576.0 | 115.2 | 172.8 | 144.0 | 1008.0 | 588.0

## Sheet2
Particulars | Effort
Development | 576
Design | 115.2
Testing | 172.8
BA | 144